## Sheet1
Ref | Description | Current Status | Action | Who to lead action | Priority
1 | 20 is Plenty for Sandgate | KCC has stated support for a 20mph scheme through the Village (August 2024). Include concerns about High Street Zebra Crossing and lack of a dropped kerb between 99 High Street and Tower Court as part of any scheme. | Need to work on the funding. | Tim & Susan | High
2 | Sea water quality testing | Water testing undertaken October 2023 to January 2024. Report published 12 March 2024 and open letter sent 4 April 2024. SW: "we do not have any plans to extend the sewage outfall pipe at Granville Parade as the Sandgate area is already achieving the Government's target." DEFRA website: "The Bathing Water Regulations and application guidance are currently being revised. During this time, Defra is not accepting applications for bathing water designation. We expect to begin accepting applications again in spring 2025." | Need to do what we can to get an Application for Spring 2025 Signs to be put up about sea water quality (Sept 2024) | Peter | High
3 | Introduction of solar panels onto assets for clean, renewable energy, starting with the Boat House | Liaising with UK Power Networks who own a section of the roof | Planning Application submitted | Gaye | High
4 | Greening: wilding, planters, hanging baskets and tree planting | Wildflower seeds sown in Sandgate Park on 30 January 2024. Need to monitor. Ongoing correspondence with architects about tree planting (to replace those lost by development on Military Road). How best to water hanging baskets etc. | Roland and Katrina Brown of Hearts Delight Farm near Barham can provide wildflower consultancy and supply seeds - worth contacting them? Also kentwildflowerseeds.co.uk | Rosa & Nicola | High
5 | Sandgate Sprucing | Form a partnership with the Folkestone Sprucers and develop a Sandgate Hub with a list for action: repaint 2 telephone cabinets (High Street and Eplanade), overgrown paths (Encombe to Wilberforce Road Car Park, Jacob's Ladder Path from Girls School to Sandgate Hill), metal bins in village (rub down and paint), benches (rub down and treat), Military Road weeds along park side of the wall etc. | Susan met with Jon Aug 2024. Need to form a list and identify some volunteers. Meeting SEA 11 Sept. | Susan & Rosa | High
6 | Enhance the provision of play equipment, seating and structures in parks and open areas | Lottery Funding application (£20k in September) successful. The lottery monies along with CIL monies has been allocated to the play surfaces in both parks, so that they are completely replaced and colourful, with the exception of the area around the play tower on Sandgate park which does not need replacing (yet). | Play surfaces to be installed shortly | Gaye | Medium
7 | Identidy options to enhance cycle parking e.g. in Council car parks, at the front of the Library, on Sandgate High St | Cycle parking stands added to the Village Green (August 2024). | Consider other options e.g. by the Rowing Club (but not our land and unregistered), improve the cycle parking by the Library etc. | Susan | Medium
8 | Missing dropped kerbs in Enbrook Valley | Nine areas have been identified that require dropped kerbs - all within half a mile of the shopping centre | Add location of areas to HIP and discuss at HIP meeting | Nicola & Susan | Medium
9 | Identify junctions which are difficult to cross and could be improved e.g. Military Road at junction with Sandgate High St; Coolinge Lane at junction with Sandgate Hill | Pedestrian refuge island at the bottom of Military Road added to HIP | In the HIP, needs funding. Discuss at HIP meeting | Susan | Medium
10 | Enbrook Valley Road (near Fremantle Park) has zero kerb delineation up one side - need bollards to prevent this. | Road is now an approved Speedwatch site. | Gaye has chased KCC re bollards (August 2024) | Gaye | Medium
11 | Escarpment walking routes are poorly signposted as to destination and often badly made | They need improving (the developer owner should do it) | Gaye reminded the developers August 2024 | Gaye & Rosa | Medium
12 | "Solarium" area by the Moore Memorial | Difficult to come up with a proposal given that the area is covered by pebbles a few times a year. | Continue to try and and think of a workable proposal | Rosa & Gaye | Low
13 | Toilets in Sandgate Park | SPC does not have funds to introduce toilets in Sandgate Park, but would support their introduction if funding can be found elsewhere |  | Susan | Low